## Tabelle1
Risk Management
Risk Name | Description | Probability | Damage | Factor | Mitigation | Person in Charge
Lack of communication | Coronavirus preventing us from meeting in person | 98.57% | 7 | 6.8999 | Increase frequency of online meetings, use tools for tele-presence | Michaela
Not enough time | Deadline comes before game is finished | 15% | 45 | 6.75 | Make a realistic roadmap and be ready to drop features to free up time | Daniel & Michaela
Game does not work properly | Bugs and/or bad performance make the game unplayable | 10% | 60 | 6 | Keep track of code errors and communicate about them transparently | David & Gabriel
Rejection | Users don't like the game after testing it | 2.5% | 200 | 5 | Make it appealing and enjoying to play | Daniel & Gabriel
Lack of interest | Users aren't interested in obtaining the game | 1% | 400 | 4 | Good external communication and advertisement | David
Key tool breaks down | High usage due to Coronavirus overloads internet infrastructure | 0.5% | 690 | 3.45 | Use well-established tools with a high quality and reliable backend | Michaela
World's end | No progress possible, potential death of team members | 0.001% | 69420 | 0.6942 | If it happens, there are other problems, therefore it's not worth tracking | Nobody